## Sheet1
For Client - Parking Violations
I | N | V | E | S | T | Priority | Sprint Number | Story number | Story | Acceptance Criteria | Story Points | Notes | Estimate
[6 empty] | M | 1 | 1 | As a student/faculty member I want to have access to a permit registration system so I can request a permit online | Option to select between student or faculty member. User input field for personal information (name, date of birth, address (optional), email address. Option to pick up permit rather than have it delievered. User input field for vehicle information (vehicle type (2/4/other wheel number), vehicle registration information). | 3
[6 empty] | M | 1 | 2 | As a faculty member I need to have access to a permit registration system so that I can request a guest permit online lasting hourly/daily/monthly/yearly | User selection option for hourly/daily/monthly/yearly available during academic guest permit request form | 1
[6 empty] | M | 3 | 3 | As an OHS faculty member I want to have access to a current outstanding applications so that I can approve/decline parking permits | Can view permit submission database, along with submitter information via dashboard | 3
[6 empty] | M | 1 | 4 | As a patrol officer I'd like to be able to record parking/smoking/other violator information so that I can issue fines | Option to choose between parking, smoking or "other" citation form. User input form containing citation number, date & time of violation, and description of violation. Smoking violation form contains violator name, department violator belongs to, violator supervisor, location of violation. Parking violation form has option for permit/no permit, permit number, vehicle registration info, vehicle type. Final violation form for other. | 4
[6 empty] | M | 1 | 5 | As a recipient of a fine I would like an online payment system so that I can easily pay my fines. | User input field to input fine number Second user input form for inputting payment information (CC number/expiry) Confirmation screen notifying the user that they will be contacted when payment is processed. | 4
[6 empty] | S | 2 | 6 | As a student/faculty member I need access to a permit length option so that I can choose between a weekly/monthly/yearly permit | User selection option for weekly/monthly (student) and monthly/yearly (faculty member) for respective permit applicants during permit request form | 1 | Potential Permit holder?
[6 empty] | S | 1 | 7 | As a parking permit holder I'd like access to a parking ToS so that I'm aware of the QUT parking rules | Terms of Service should be accessible at any time via parking website | 1
[6 empty] | S | 2 | 8 | As a college personnel/student who has discovered a potential OHS hazard I would like a way to report the issue so that the campus is safer. | User input form to report personal information (name, student number, email/phone number (optional information if the reporter wants updates), hazard description and location of hazard | 2
[6 empty] | S | 2 | 9 | As an issuer of permits I would like permit recipients to accept the parking ToS during their permit application to reduce the likelyhood of violations. | Terms of Service should be shown with an accept/do not accept option before the final permit submission screen | 1
[6 empty] | S | 4 | 10 | As a parking officer I'd like permits to have some form of identification code so that I can easily validate them | Creation of parking permits include a QR code which link to the permit information | 2
[6 empty] | S | 3 | 11 | As an OHS faculty member I want access to a database containing fines so that I can issue them to violators | OHS faculty member has access to fine databse (read-only permission) | 3
[6 empty] | S | 5 | 12 | As a parking permit holder I'd like to be able to purchase a premium permit upgrade that guarantees me the same parking spot everyday so that I don't have to look for a new one everytime I park | User input form containing fields for user's permit information Option to upgrade to premium after permit registeration/before payment Monthly/yearly permit options (college personnel only) Distribution and expiration on first day of the month | 1
[6 empty] | C | 4 | 13 | As a permit holder i would like to recieve a noification when my permit is due to expire | Automatic reminder system that sends out emails to permit holders based on their permit types and how long is remaining - When less than 20% (+/-10%) of parking time is available send user a warning notification. | 1
[6 empty] | C | 5 | 14 | As someone who reported an OHS issue I'd like to be able to track it's progress so that I know when the issue's been solved | System automatically sends out an email to an issue's reporter whenever it's progress is updated. | 2
[6 empty] | C | 6 | 15 | As a parking user I'd like to see parking availability through google maps so that I know where to park in advance | Map of parking spots integrated with Google Maps showing availability in real time | 5
[6 empty] | C | 6 | 16 | As a permit holder I'd like to be able to reserve a parking spot in advance so that I don't need to waste time driving through the carpark | User input field for parking permit information (number and type (student/staff/guest)) as well as interactive parking availability map allowing the user to select an available spot. Second input field containing forms regarding requested parking date and time (from & to) | 5
[6 empty] | C | 4 | 17 | As a recipient of a fine I would like an easy way to contest and request a review. | User input form for putting in name, fine number and reason for contesting | 1
[6 empty] | C | 5 | 18 | As a patrol officer I would like to be able to capture photographic evidence of violators and attach it to the citation. | Mobile patrol application with input fields to put in violation, violator information Camera function for attaching images of violator & violation (in some cases) | 5
[6 empty] | C | 4 | 19 | As an academic visitor, I would like to easily apply for a hourly/daily/monthly/yearly permit online so that I can attend events. | User input form to input visitor information and permit length requested | 2
[6 empty] | C | 6 | 20 | As a visitor, I would like access to a chauffeur so that I do not have to waste time parking | User input form to request chauffeur containing permit information, car information (make/model/colour/rego) and estimated arrival time | 2
[6 empty] | C | 3 | 21 | As an OHS faculty member I need to be able to review submitted OHS hazard reports so that I can discard them or enter them into the active report database | Access through OHS faculty dashboard showing all reports with option to accept or reject them | 3
[6 empty] | C | 4 | 22 | As an OHS faculty member (maintenance crew) I need access to the active report database so that I can complete maintanence tasks | Maintenance crew member has access to active report database (read-only permission) | 3
[6 empty] | C | 4 | 23 | As an OHS faculty member (maintenance crew) I need access to a system that lets me log resolved issues so that I can record when and how an OHS issue has been resolved | Maintenance crew member can access user input form with fields for how and when the issue was resolved | 3
[6 empty] | C | 3 | 24 | As a parking permit holder I need to be able to report lost or stolen parking permits so I can receive a new one | User input form with fields for permit holder name, permit number, DoB, and address An email will be sent out to the permit holder with a reference number to finalise the request/report | 1
[6 empty] | C | 6 | 25 | As a parking permit holder I'd like a notifcation screen implemented outside of the parking area reporting on traffic levels so that I know which route to take | Screen outside of parking building connected to OHS dashboard Dashboard function with user input field for screen text (for notifications/warnings) | 5
[6 empty] | C | 4 | 26 | As an OHS faculty member I'd like to be able to send out severe weather notifications to parking permit holders as a courtesy | Dashboard function allowing OHS faculty members to send out a weather warning SMS to permit holders signed up for the weather notification service | 3
[6 empty] | C | 6 | 27 | As a parking permit holder I'd like to be able to reserve a storage locker in advance online so that I don't have to carry my belongings around campus | Application on parking website allowing permit holders to reserve a storage locker | 3
[6 empty] | C | 6 | 28 | As a premium parking permit holder I'd to be able to transfer my premium upgrade to another permit holder so that the parking space isn't wasted | User input form containing fields for user's permit information and transferee's permit information. Requires approval from an OHS faculty member Email is sent out to transferer and transferee confirming the upgrade transfer | 5
[6 empty] | C | 6 | 29 | As a premium parking permit holder I'd like to be able to add or remove cars from my permit so that multiple cars are eligible to use my parking space | Webpage showing currently registered cars in a table with options to remove Separate input form for adding extra cars (fields for inputting car information) Limit of 5 cars per permit | 5
[6 empty] | c | 3 | 30 | As an OHS faculty member I want to be able to access a payment tracking system so that I can follow up outstanding fines | Can view outstanding fine information by inputting registration info/fine number through a function on the dashboard | 3